## Sheet1
Milestones | Tasks | Percentage of Completion | Start Date | Duration
Design | Acclimate to Technology | 100% | 2017-01-24 | 14
| Design site pages | 100% | 2017-01-24 | 7
| Design DB | 80% | 2017-01-24 | 7
| Design API | 75% | 2017-01-24 | 7
Development | Setup Services + DevOps | 30% | 2017-02-07 | 7
| Write HTML/Aesthetic code | 10% | 2017-02-07 | 28
| Write functional JS CRUD | 5% | 2017-02-07 | 28
| Write middleware API | 5% | 2017-02-07 | 28
| Write DB tables/schema | 5% | 2017-02-07 | 28
Testing | Write middleware API | 0% | 2017-03-07 | 14
| Test JS with DB tables | 0% | 2017-03-07 | 7
| Deploy to webserver | 0% | 2017-03-07 | 7 | Critical Path: Critical path is illustrated by the orange bars.
| Security analysis/terms of use | 0% | 2017-03-07 | 14
Implementation | Optimise webserver for security | 0% | 2017-03-21 | 14
| Write automated test cases | 0% | 2017-03-21 | 7
| Deploy to production AWS | 0% | 2017-03-21 | 7